## experts
Name | Comment
PM.Daniel | the 1st unit
PM.Angel | the 1st unit
DEV.Paul | the 1st unit
SA.Adrian | the 1st unit
SA.Robert | the 1st unit
DEV.Hugo | the 1st unit
DEV.Frances | the 1st unit
DEV.Tom | the 1st unit
PM.Lisa | the 1st unit
DEV.Charles | the 1st unit
DEV.Francis | the 1st unit
DEV.Carl | the 1st unit
DEV.Lars | the 1st unit
DEV.Martin | the 1st unit
DEV.Michael | the 1st unit

## tasks
Name | Start day | End day | Work
alpha.m | 2025-01-01 | 2025-04-01 | 450
alpha.f | 2025-04-02 | 2025-05-02 | 60
alpha.pm | 2025-01-01 | 2025-04-01 | 45
alpha.pf | 2025-04-02 | 2025-05-02 | 5
alpha.sm | 2025-01-01 | 2025-04-01 | 10
alpha.sf | 2025-04-02 | 2025-05-02 | 5
beta.m | 2025-01-01 | 2025-06-20 | 650
beta.f | 2025-06-21 | 2025-08-05 | 30
beta.pm | 2025-01-01 | 2025-06-20 | 65
beta.pf | 2025-06-21 | 2025-08-05 | 5
beta.sm | 2025-01-01 | 2025-06-20 | 10
beta.sf | 2025-06-21 | 2025-08-05 | 5
charlie.m | 2025-01-01 | 2025-06-05 | 800
charlie.f | 2025-06-06 | 2025-07-06 | 100
charlie.pm | 2025-01-01 | 2025-06-05 | 80
charlie.pf | 2025-06-06 | 2025-07-06 | 10
charlie.sm | 2025-01-01 | 2025-06-05 | 15
charlie.sf | 2025-06-06 | 2025-07-06 | 5
delta.m | 2025-01-01 | 2025-02-25 | 220
delta.f | 2025-02-26 | 2025-04-12 | 20
delta.pm | 2025-01-01 | 2025-02-25 | 25
delta.pf | 2025-02-26 | 2025-04-12 | 5
delta.sm | 2025-01-01 | 2025-02-25 | 5
delta.sf | 2025-02-26 | 2025-04-12 | 5
echo.m | 2025-01-01 | 2025-03-15 | 250
echo.f | 2025-04-02 | 2025-05-17 | 25
echo.pm | 2025-01-01 | 2025-03-15 | 20
echo.pf | 2025-04-02 | 2025-05-17 | 5
echo.sm | 2025-01-01 | 2025-03-15 | 5
echo.sf | 2025-04-02 | 2025-05-17 | 8
foxtrot.m | 2025-01-01 | 2025-04-01 | 150
foxtrot.f | 2025-04-02 | 2025-05-02 | 25
foxtrot.pm | 2025-01-01 | 2025-04-01 | 20
foxtrot.pf | 2025-04-02 | 2025-05-02 | 5
foxtrot.sm | 2025-01-01 | 2025-04-01 | 8
foxtrot.sf | 2025-04-02 | 2025-05-02 | 8
golf.m | 2025-01-01 | 2025-05-12 | 350
golf.f | 2025-05-13 | 2025-06-27 | 30
golf.pm | 2025-01-01 | 2025-05-12 | 40
golf.pf | 2025-05-13 | 2025-06-27 | 10
golf.sm | 2025-01-01 | 2025-05-12 | 10
golf.sf | 2025-05-13 | 2025-06-27 | 8
hotel.m | 2025-01-01 | 2025-09-01 | 750
hotel.f | 2025-09-02 | 2025-10-17 | 70
hotel.pm | 2025-01-01 | 2025-09-01 | 80
hotel.pf | 2025-09-02 | 2025-10-17 | 10
hotel.sm | 2025-01-01 | 2025-09-01 | 15
hotel.sf | 2025-09-02 | 2025-10-17 | 5
india.m | 2025-01-01 | 2025-10-01 | 1100
india.f | 2025-10-02 | 2025-11-01 | 200
india.pm | 2025-01-01 | 2025-10-01 | 130
india.pf | 2025-10-02 | 2025-11-01 | 25
india.sm | 2025-01-01 | 2025-10-01 | 30
india.sf | 2025-10-02 | 2025-11-01 | 12
juliet.e | 2025-02-10 | 2025-02-27 | 10
juliet.m | 2025-02-28 | 2025-06-30 | 450
juliet.f | 2025-07-01 | 2025-08-15 | 35
juliet.pe | 2025-02-10 | 2025-02-27 | 10
juliet.pm | 2025-02-28 | 2025-06-30 | 50
juliet.pf | 2025-07-01 | 2025-08-15 | 5
juliet.se | 2025-02-10 | 2025-02-27 | 10
juliet.sm | 2025-02-28 | 2025-06-30 | 10
juliet.sf | 2025-07-01 | 2025-08-15 | 5
kilo.e | 2025-03-01 | 2025-03-24 | 20
kilo.m | 2025-03-25 | 2025-08-01 | 550
kilo.f | 2025-08-02 | 2025-09-16 | 40
kilo.pe | 2025-03-01 | 2025-03-24 | 10
kilo.pm | 2025-03-25 | 2025-08-01 | 50
kilo.pf | 2025-08-02 | 2025-09-16 | 5
kilo.se | 2025-03-01 | 2025-03-24 | 15
kilo.sm | 2025-03-25 | 2025-08-01 | 10
kilo.sf | 2025-08-02 | 2025-09-16 | 5
lima.e | 2023-03-21 | 2024-04-19 | 30
lima.m | 2025-04-20 | 2025-11-01 | 1050
lima.f | 2025-11-02 | 2025-11-30 | 120
lima.pe | 2023-03-21 | 2024-04-19 | 25
lima.pm | 2024-04-20 | 2025-11-01 | 100
lima.pf | 2025-11-02 | 2025-11-30 | 20
lima.se | 2023-03-21 | 2024-04-19 | 36
lima.sm | 2024-04-20 | 2025-11-01 | 10
lima.sf | 2025-11-02 | 2025-11-30 | 5
mike.e | 2025-04-10 | 2025-04-20 | 10
mike.m | 2025-04-25 | 2025-09-25 | 450
mike.f | 2025-09-26 | 2025-10-30 | 60
mike.pe | 2025-04-10 | 2025-04-20 | 10
mike.pm | 2025-04-21 | 2025-09-25 | 50
mike.pf | 2025-09-26 | 2025-10-30 | 5
mike.se | 2025-04-10 | 2025-04-20 | 15
mike.sm | 2025-04-21 | 2025-09-25 | 10
mike.sf | 2025-09-26 | 2025-10-30 | 5
november.e | 2025-05-26 | 2025-06-14 | 10
november.m | 2025-06-15 | 2025-12-30 | 550
november.f | 2025-12-31 | 2026-01-31 | 30
november.pe | 2025-05-26 | 2025-06-14 | 10
november.pm | 2025-06-15 | 2025-12-30 | 55
november.pf | 2025-12-31 | 2026-01-31 | 5
november.se | 2025-05-26 | 2025-06-14 | 10
november.sm | 2025-06-15 | 2025-12-30 | 10
november.sf | 2025-12-31 | 2026-01-31 | 5
oscar.e | 2025-06-25 | 2025-07-09 | 15
oscar.m | 2025-07-10 | 2025-12-30 | 600
oscar.f | 2025-12-31 | 2026-01-31 | 40
oscar.pe | 2025-06-25 | 2025-07-09 | 15
oscar.pm | 2025-07-10 | 2025-12-30 | 70
oscar.pf | 2025-12-31 | 2026-01-31 | 10
oscar.se | 2025-06-25 | 2025-07-09 | 10
oscar.sm | 2025-07-10 | 2025-12-30 | 10
oscar.sf | 2025-12-31 | 2026-01-31 | 8
Formulas:
Start day = [End day, row above]+1
End day = [Start day]+30
End day = [Start day, row below]-1

## links
Expert | Task
PM.Daniel | alpha.pm
PM.Daniel | alpha.pf
PM.Daniel | beta.pm
PM.Daniel | beta.pf
PM.Angel | charlie.pm
PM.Angel | charlie.pf
PM.Angel | delta.pm
PM.Angel | delta.pf
PM.Lisa | echo.pm
PM.Lisa | echo.pf
PM.Lisa | foxtrot.pm
PM.Lisa | foxtrot.pf
PM.Lisa | golf.pm
PM.Lisa | golf.pf
PM.Lisa | hotel.pm
PM.Lisa | hotel.pf
PM.Daniel | india.pm
PM.Daniel | india.pf
PM.Angel | juliet.pe
PM.Angel | juliet.pm
PM.Angel | juliet.pf
PM.Lisa | kilo.pe
PM.Lisa | kilo.pm
PM.Lisa | kilo.pf
PM.Lisa | lima.pe
PM.Lisa | lima.pm
PM.Lisa | lima.pf
PM.Angel | mike.pe
PM.Angel | mike.pm
PM.Angel | mike.pf
PM.Angel | november.pe
PM.Angel | november.pm
PM.Angel | november.pf
PM.Daniel | oscar.pe
PM.Daniel | oscar.pm
PM.Daniel | oscar.pf
DEV.Paul | alpha.m
DEV.Paul | alpha.f
SA.Adrian | alpha.m
SA.Adrian | alpha.f
DEV.Hugo | alpha.m
DEV.Hugo | alpha.f
SA.Robert | beta.m
SA.Robert | beta.f
DEV.Frances | beta.m
DEV.Frances | beta.f
DEV.Tom | beta.m
DEV.Tom | beta.f
DEV.Charles | charlie.m
DEV.Charles | charlie.f
DEV.Francis | charlie.m
DEV.Francis | charlie.f
DEV.Carl | charlie.m
DEV.Carl | charlie.f
DEV.Paul | charlie.m
DEV.Paul | charlie.f
DEV.Lars | delta.m
DEV.Lars | delta.f
DEV.Martin | echo.m
DEV.Martin | echo.f
DEV.Michael | foxtrot.m
DEV.Michael | foxtrot.f
SA.Adrian | golf.m
SA.Adrian | golf.f
DEV.Hugo | golf.m
DEV.Hugo | golf.f
DEV.Francis | hotel.m
DEV.Francis | hotel.f
DEV.Martin | hotel.m
DEV.Martin | hotel.f
DEV.Michael | hotel.m
DEV.Michael | hotel.f
DEV.Paul | india.m
DEV.Paul | india.f
SA.Robert | india.m
SA.Robert | india.f
DEV.Lars | india.m
DEV.Lars | india.f
DEV.Charles | india.m
DEV.Charles | india.f
DEV.Tom | india.m
DEV.Tom | india.f
DEV.Carl | juliet.m
DEV.Carl | juliet.f
DEV.Hugo | juliet.m
DEV.Hugo | juliet.f
DEV.Martin | kilo.m
DEV.Martin | kilo.f
DEV.Francis | kilo.m
DEV.Francis | kilo.f
DEV.Paul | lima.m
DEV.Paul | lima.f
DEV.Frances | lima.m
DEV.Frances | lima.f
DEV.Michael | lima.m
DEV.Michael | lima.f
SA.Adrian | lima.m
SA.Adrian | lima.f
DEV.Martin | mike.m
DEV.Martin | mike.f
DEV.Michael | mike.m
DEV.Michael | mike.f
DEV.Carl | november.m
DEV.Carl | november.f
DEV.Hugo | november.m
DEV.Hugo | november.f
SA.Robert | oscar.m
SA.Robert | oscar.f
DEV.Tom | oscar.m
DEV.Tom | oscar.f
DEV.Michael | alpha.sm
DEV.Michael | alpha.sf
DEV.Carl | beta.sm
DEV.Carl | beta.sf
SA.Adrian | charlie.sm
SA.Adrian | charlie.sf
DEV.Hugo | delta.sm
DEV.Hugo | delta.sf
SA.Adrian | echo.sm
SA.Adrian | echo.sf
SA.Robert | foxtrot.sm
SA.Robert | foxtrot.sf
SA.Robert | golf.sm
SA.Robert | golf.sf
SA.Robert | hotel.sm
SA.Robert | hotel.sf
DEV.Charles | india.sm
DEV.Charles | india.sf
DEV.Charles | juliet.se
DEV.Charles | juliet.sm
DEV.Charles | juliet.sf
DEV.Paul | kilo.se
DEV.Paul | kilo.sm
DEV.Paul | kilo.sf
DEV.Tom | lima.se
DEV.Tom | lima.sm
DEV.Tom | lima.sf
DEV.Frances | mike.se
DEV.Frances | mike.sm
DEV.Frances | mike.sf
DEV.Frances | november.se
DEV.Frances | november.sm
DEV.Frances | november.sf
DEV.Paul | oscar.se
DEV.Paul | oscar.sm
DEV.Paul | oscar.sf
PM.Daniel | juliet.e
PM.Daniel | kilo.e
PM.Daniel | mike.e
PM.Daniel | november.e
PM.Daniel | oscar.e

## xbday
Expert | Task | Start day | End day | Lower | Upper

## xbsum
Expert | Task | Start day | End day | Lower | Upper

## ubday
Expert | Start day | End day | Lower | Upper

## ubsum
Expert | Task | Start day | End day | Lower | Upper

## expert bounds
Expert | Start day | End day | Lower | Upper

## invoicing periods
Name | Start day | End day
January.2025 | 2024-12-11 | 2025-01-15
February.2025 | 2025-01-16 | 2025-02-13
March.2025 | 2025-02-14 | 2025-03-16
April.2025 | 2025-03-17 | 2025-04-14
May.2025 | 2025-04-15 | 2025-05-18
June.2025 | 2025-05-19 | 2025-06-18
July.2025 | 2025-06-19 | 2025-07-17
August.2025 | 2025-07-18 | 2025-08-17
September.2025 | 2025-08-18 | 2025-09-15
October.2025 | 2025-09-16 | 2025-10-15
November.2025 | 2025-10-16 | 2025-11-12
December.2025 | 2025-11-13 | 2025-12-11

## invoicing periods bounds
Expert | Period | Lower | Upper
PM.Daniel | January.2025 | 0 | 180
PM.Daniel | February.2025 | 0 | 180
PM.Daniel | March.2025 | 0 | 180
PM.Daniel | April.2025 | 0 | 180
PM.Daniel | May.2025 | 0 | 180
PM.Daniel | June.2025 | 0 | 180
PM.Daniel | July.2025 | 0 | 180
PM.Daniel | August.2025 | 0 | 180
PM.Daniel | September.2025 | 0 | 180
PM.Daniel | October.2025 | 0 | 180
PM.Daniel | November.2025 | 0 | 180
PM.Daniel | December.2025 | 0 | 180
PM.Angel | January.2025 | 0 | 180
PM.Angel | February.2025 | 0 | 180
PM.Angel | March.2025 | 0 | 180
PM.Angel | April.2025 | 0 | 180
PM.Angel | May.2025 | 0 | 180
PM.Angel | June.2025 | 0 | 180
PM.Angel | July.2025 | 0 | 180
PM.Angel | August.2025 | 0 | 180
PM.Angel | September.2025 | 0 | 180
PM.Angel | October.2025 | 0 | 180
PM.Angel | November.2025 | 0 | 180
PM.Angel | December.2025 | 0 | 180
DEV.Paul | January.2025 | 0 | 180
DEV.Paul | February.2025 | 0 | 180
DEV.Paul | March.2025 | 0 | 180
DEV.Paul | April.2025 | 0 | 180
DEV.Paul | May.2025 | 0 | 180
DEV.Paul | June.2025 | 0 | 180
DEV.Paul | July.2025 | 0 | 180
DEV.Paul | August.2025 | 0 | 180
DEV.Paul | September.2025 | 0 | 180
DEV.Paul | October.2025 | 0 | 180
DEV.Paul | November.2025 | 0 | 180
DEV.Paul | December.2025 | 0 | 180
SA.Adrian | January.2025 | 0 | 180
SA.Adrian | February.2025 | 0 | 180
SA.Adrian | March.2025 | 0 | 180
SA.Adrian | April.2025 | 0 | 180
SA.Adrian | May.2025 | 0 | 180
SA.Adrian | June.2025 | 0 | 180
SA.Adrian | July.2025 | 0 | 180
SA.Adrian | August.2025 | 0 | 180
SA.Adrian | September.2025 | 0 | 180
SA.Adrian | October.2025 | 0 | 180
SA.Adrian | November.2025 | 0 | 180
SA.Adrian | December.2025 | 0 | 180
SA.Robert | January.2025 | 0 | 180
SA.Robert | February.2025 | 0 | 180
SA.Robert | March.2025 | 0 | 180
SA.Robert | April.2025 | 0 | 180
SA.Robert | May.2025 | 0 | 180
SA.Robert | June.2025 | 0 | 180
SA.Robert | July.2025 | 0 | 180
SA.Robert | August.2025 | 0 | 180
SA.Robert | September.2025 | 0 | 180
SA.Robert | October.2025 | 0 | 180
SA.Robert | November.2025 | 0 | 180
SA.Robert | December.2025 | 0 | 180
DEV.Hugo | January.2025 | 0 | 180
DEV.Hugo | February.2025 | 0 | 180
DEV.Hugo | March.2025 | 0 | 180
DEV.Hugo | April.2025 | 0 | 180
DEV.Hugo | May.2025 | 0 | 180
DEV.Hugo | June.2025 | 0 | 180
DEV.Hugo | July.2025 | 0 | 180
DEV.Hugo | August.2025 | 0 | 180
DEV.Hugo | September.2025 | 0 | 180
DEV.Hugo | October.2025 | 0 | 180
DEV.Hugo | November.2025 | 0 | 180
DEV.Hugo | December.2025 | 0 | 180
DEV.Frances | January.2025 | 0 | 180
DEV.Frances | February.2025 | 0 | 180
DEV.Frances | March.2025 | 0 | 180
DEV.Frances | April.2025 | 0 | 180
DEV.Frances | May.2025 | 0 | 180
DEV.Frances | June.2025 | 0 | 180
DEV.Frances | July.2025 | 0 | 180
DEV.Frances | August.2025 | 0 | 180
DEV.Frances | September.2025 | 0 | 180
DEV.Frances | October.2025 | 0 | 180
DEV.Frances | November.2025 | 0 | 180
DEV.Frances | December.2025 | 0 | 180
DEV.Tom | January.2025 | 0 | 180
DEV.Tom | February.2025 | 0 | 180
DEV.Tom | March.2025 | 0 | 180
DEV.Tom | April.2025 | 0 | 180
DEV.Tom | May.2025 | 0 | 180
DEV.Tom | June.2025 | 0 | 180
DEV.Tom | July.2025 | 0 | 180
DEV.Tom | August.2025 | 0 | 180
DEV.Tom | September.2025 | 0 | 180
DEV.Tom | October.2025 | 0 | 180
DEV.Tom | November.2025 | 0 | 180
DEV.Tom | December.2025 | 0 | 180
PM.Lisa | January.2025 | 0 | 180
PM.Lisa | February.2025 | 0 | 180
PM.Lisa | March.2025 | 0 | 180
PM.Lisa | April.2025 | 0 | 180
PM.Lisa | May.2025 | 0 | 180
PM.Lisa | June.2025 | 0 | 180
PM.Lisa | July.2025 | 0 | 180
PM.Lisa | August.2025 | 0 | 180
PM.Lisa | September.2025 | 0 | 180
PM.Lisa | October.2025 | 0 | 180
PM.Lisa | November.2025 | 0 | 180
PM.Lisa | December.2025 | 0 | 180
DEV.Charles | January.2025 | 0 | 180
DEV.Charles | February.2025 | 0 | 180
DEV.Charles | March.2025 | 0 | 180
DEV.Charles | April.2025 | 0 | 180
DEV.Charles | May.2025 | 0 | 180
DEV.Charles | June.2025 | 0 | 180
DEV.Charles | July.2025 | 0 | 180
DEV.Charles | August.2025 | 0 | 180
DEV.Charles | September.2025 | 0 | 180
DEV.Charles | October.2025 | 0 | 180
DEV.Charles | November.2025 | 0 | 180
DEV.Charles | December.2025 | 0 | 180
DEV.Francis | January.2025 | 0 | 180
DEV.Francis | February.2025 | 0 | 180
DEV.Francis | March.2025 | 0 | 180
DEV.Francis | April.2025 | 0 | 180
DEV.Francis | May.2025 | 0 | 180
DEV.Francis | June.2025 | 0 | 180
DEV.Francis | July.2025 | 0 | 180
DEV.Francis | August.2025 | 0 | 180
DEV.Francis | September.2025 | 0 | 180
DEV.Francis | October.2025 | 0 | 180
DEV.Francis | November.2025 | 0 | 180
DEV.Francis | December.2025 | 0 | 180
DEV.Carl | January.2025 | 0 | 180
DEV.Carl | February.2025 | 0 | 180
DEV.Carl | March.2025 | 0 | 180
DEV.Carl | April.2025 | 0 | 180
DEV.Carl | May.2025 | 0 | 180
DEV.Carl | June.2025 | 0 | 180
DEV.Carl | July.2025 | 0 | 180
DEV.Carl | August.2025 | 0 | 180
DEV.Carl | September.2025 | 0 | 180
DEV.Carl | October.2025 | 0 | 180
DEV.Carl | November.2025 | 0 | 180
DEV.Carl | December.2025 | 0 | 180
DEV.Lars | January.2025 | 0 | 180
DEV.Lars | February.2025 | 0 | 180
DEV.Lars | March.2025 | 0 | 180
DEV.Lars | April.2025 | 0 | 180
DEV.Lars | May.2025 | 0 | 180
DEV.Lars | June.2025 | 0 | 180
DEV.Lars | July.2025 | 0 | 180
DEV.Lars | August.2025 | 0 | 180
DEV.Lars | September.2025 | 0 | 180
DEV.Lars | October.2025 | 0 | 180
DEV.Lars | November.2025 | 0 | 180
DEV.Lars | December.2025 | 0 | 180
DEV.Martin | January.2025 | 0 | 180
DEV.Martin | February.2025 | 0 | 180
DEV.Martin | March.2025 | 0 | 180
DEV.Martin | April.2025 | 0 | 180
DEV.Martin | May.2025 | 0 | 180
DEV.Martin | June.2025 | 0 | 180
DEV.Martin | July.2025 | 0 | 180
DEV.Martin | August.2025 | 0 | 180
DEV.Martin | September.2025 | 0 | 180
DEV.Martin | October.2025 | 0 | 180
DEV.Martin | November.2025 | 0 | 180
DEV.Martin | December.2025 | 0 | 180
DEV.Michael | January.2025 | 0 | 180
DEV.Michael | February.2025 | 0 | 180
DEV.Michael | March.2025 | 0 | 180
DEV.Michael | April.2025 | 0 | 180
DEV.Michael | May.2025 | 0 | 180
DEV.Michael | June.2025 | 0 | 180
DEV.Michael | July.2025 | 0 | 180
DEV.Michael | August.2025 | 0 | 180
DEV.Michael | September.2025 | 0 | 180
DEV.Michael | October.2025 | 0 | 180
DEV.Michael | November.2025 | 0 | 180
DEV.Michael | December.2025 | 0 | 180

## public holidays
Date
2024-12-24
2024-12-25
2024-12-26
2025-01-01
2025-04-20
2025-01-01

## misc
Today | Hours per day | dpi | T:start | T:end | H:start | H:end | Solver
2024-12-30 | 8 | 150 | 2025-01-01 | 2026-01-31 | 2025-01-01 | 2026-01-31 | highs