## experts
Name | Comment
Bożydar | Solution Architect role

## tasks
Name | Start | End | Work
p2.e | 2024-11-21 | 2024-12-04 | 40
p2.m | 2024-12-05 | 2025-04-02 | 85
p2.f | 2025-04-03 | 2025-04-30 | 40
p3.e | 2024-12-01 | 2024-12-13 | 20
p3.m | 2024-12-14 | 2025-05-30 | 105
p3.f | 2025-05-31 | 2025-06-27 | 40
p4.e | 2024-12-16 | 2025-01-03 | 45
p4.m | 2025-01-04 | 2025-06-20 | 105
p4.f | 2025-06-21 | 2025-07-18 | 40
p5.e | 2024-12-31 | 2025-01-13 | 40
p5.m | 2025-01-14 | 2025-05-12 | 85
p5.f | 2025-05-13 | 2025-06-09 | 40
p6.e | 2025-01-20 | 2025-02-14 | 20
p6.m | 2025-02-15 | 2025-08-01 | 105
p6.f | 2025-08-02 | 2025-08-29 | 40

## links
Expert | Task
Bożydar | p2.e
Bożydar | p2.m
Bożydar | p2.f
Bożydar | p3.e
Bożydar | p3.m
Bożydar | p3.f
Bożydar | p4.e
Bożydar | p4.m
Bożydar | p4.f
Bożydar | p5.e
Bożydar | p5.m
Bożydar | p5.f
Bożydar | p6.e
Bożydar | p6.m
Bożydar | p6.f

## xbday
Expert | Task | Start | End | Lower | Upper
Bożydar | p2.e | 2024-11-21 | 2024-12-04 | 3 | 5
Bożydar | p2.m | 2024-12-05 | 2025-04-02 | 0 | 2
Bożydar | p2.f | 2025-04-03 | 2025-04-30 | 2 | 2
Bożydar | p3.e | 2024-12-01 | 2024-12-13 | 1 | 3
Bożydar | p3.m | 2024-12-14 | 2025-05-30 | 0 | 1
Bożydar | p3.f | 2025-05-31 | 2025-06-27 | 2 | 2
Bożydar | p4.e | 2024-12-16 | 2025-01-03 | 3 | 4
Bożydar | p4.m | 2025-01-04 | 2025-06-20 | 0 | 1
Bożydar | p4.f | 2025-06-21 | 2025-07-18 | 2 | 2
Bożydar | p5.e | 2024-12-31 | 2025-01-13 | 4 | 4
Bożydar | p5.m | 2025-01-14 | 2025-05-12 | 0 | 2
Bożydar | p5.f | 2025-05-13 | 2025-06-09 | 2 | 2
Bożydar | p6.e | 2025-01-20 | 2025-02-14 | 0 | 2
Bożydar | p6.m | 2025-02-15 | 2025-08-01 | 0 | 1
Bożydar | p6.f | 2025-08-02 | 2025-08-29 | 2 | 2

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End
25.Jan | 2024-12-11 | 2025-01-15
25.Feb | 2025-01-16 | 2025-02-13
25.Mar | 2025-02-14 | 2025-03-16
25.Apr | 2025-03-17 | 2025-04-14
25.May | 2025-04-15 | 2025-05-18

## invoicing periods bounds
Expert | Period | Lower | Upper

## public holidays
Date
2024-12-25

## misc
Today | Hours per day | Solver | Last day
2024-11-20 | 8 | scip | 2025-06-27

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2025-06-26 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2025-06-26 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## gimg
Task's Gantt Chart | Width | Height | Dpi | Start | End | Barh:color | Barh:height | Barh:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2025-06-26 | #ff7f0e | 0.9 | 0.6 | TRUE | TRUE

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5