## experts
Name | Comment | TRUE
PM.Daniel | the 1st unit | TRUE
PM.Angel | the 1st unit | TRUE
DEV.Paul | the 1st unit | TRUE
SA.Adrian | the 1st unit | TRUE
SA.Robert | the 1st unit | TRUE
DEV.Hugo | the 1st unit | TRUE
DEV.Frances | the 1st unit | TRUE
DEV.Tom | the 1st unit | TRUE
PM.Lisa | the 1st unit | TRUE
DEV.Charles | the 1st unit | TRUE
DEV.Francis | the 1st unit | TRUE
DEV.Carl | the 1st unit | TRUE
DEV.Lars | the 1st unit | TRUE
DEV.Martin | the 1st unit | TRUE
DEV.Michael | the 1st unit | TRUE
Note on C1: Has Expert any task?

## tasks
Name | Start day | End day | Work | TRUE | TRUE | TRUE
alpha.m | 2025-01-01 | 2025-04-01 | 450 | TRUE | TRUE | TRUE
alpha.f | 2025-04-02 | 2025-05-02 | 60 | TRUE | TRUE | 1
alpha.pm | 2025-01-01 | 2025-04-01 | 45 | TRUE | TRUE | 1
alpha.pf | 2025-04-02 | 2025-05-02 | 5 | TRUE | TRUE | 1
alpha.sm | 2025-01-01 | 2025-04-01 | 10 | TRUE | TRUE | 1
alpha.sf | 2025-04-02 | 2025-05-02 | 5 | TRUE | TRUE | 1
beta.m | 2025-01-01 | 2025-06-20 | 650 | TRUE | TRUE | 1
beta.f | 2025-06-21 | 2025-08-05 | 30 | TRUE | TRUE | 1
beta.pm | 2025-01-01 | 2025-06-20 | 65 | TRUE | TRUE | 1
beta.pf | 2025-06-21 | 2025-08-05 | 5 | TRUE | TRUE | 1
beta.sm | 2025-01-01 | 2025-06-20 | 10 | TRUE | TRUE | 1
beta.sf | 2025-06-21 | 2025-08-05 | 5 | TRUE | TRUE | 1
charlie.m | 2025-01-01 | 2025-06-05 | 800 | TRUE | TRUE | 1
charlie.f | 2025-06-06 | 2025-07-06 | 100 | TRUE | TRUE | 1
charlie.pm | 2025-01-01 | 2025-06-05 | 80 | TRUE | TRUE | 1
charlie.pf | 2025-06-06 | 2025-07-06 | 10 | TRUE | TRUE | 1
charlie.sm | 2025-01-01 | 2025-06-05 | 15 | TRUE | TRUE | 1
charlie.sf | 2025-06-06 | 2025-07-06 | 5 | TRUE | TRUE | 1
delta.m | 2025-01-01 | 2025-02-25 | 220 | TRUE | TRUE | 1
delta.f | 2025-02-26 | 2025-04-12 | 20 | TRUE | TRUE | 1
delta.pm | 2025-01-01 | 2025-02-25 | 25 | TRUE | TRUE | 1
delta.pf | 2025-02-26 | 2025-04-12 | 5 | TRUE | TRUE | 1
delta.sm | 2025-01-01 | 2025-02-25 | 5 | TRUE | TRUE | 1
delta.sf | 2025-02-26 | 2025-04-12 | 5 | TRUE | TRUE | 1
echo.m | 2025-01-01 | 2025-03-15 | 250 | TRUE | TRUE | 1
echo.f | 2025-04-02 | 2025-05-17 | 25 | TRUE | TRUE | 1
echo.pm | 2025-01-01 | 2025-03-15 | 20 | TRUE | TRUE | 1
echo.pf | 2025-04-02 | 2025-05-17 | 5 | TRUE | TRUE | 1
echo.sm | 2025-01-01 | 2025-03-15 | 5 | TRUE | TRUE | 1
echo.sf | 2025-04-02 | 2025-05-17 | 8 | TRUE | TRUE | 1
foxtrot.m | 2025-01-01 | 2025-04-01 | 150 | TRUE | TRUE | 1
foxtrot.f | 2025-04-02 | 2025-05-02 | 25 | TRUE | TRUE | 1
foxtrot.pm | 2025-01-01 | 2025-04-01 | 20 | TRUE | TRUE | 1
foxtrot.pf | 2025-04-02 | 2025-05-02 | 5 | TRUE | TRUE | 1
foxtrot.sm | 2025-01-01 | 2025-04-01 | 8 | TRUE | TRUE | 1
foxtrot.sf | 2025-04-02 | 2025-05-02 | 8 | TRUE | TRUE | 1
golf.m | 2025-01-01 | 2025-05-12 | 350 | TRUE | TRUE | 1
golf.f | 2025-05-13 | 2025-06-27 | 30 | TRUE | TRUE | 1
golf.pm | 2025-01-01 | 2025-05-12 | 40 | TRUE | TRUE | 1
golf.pf | 2025-05-13 | 2025-06-27 | 10 | TRUE | TRUE | 1
golf.sm | 2025-01-01 | 2025-05-12 | 10 | TRUE | TRUE | 1
golf.sf | 2025-05-13 | 2025-06-27 | 8 | TRUE | TRUE | 1
hotel.m | 2025-01-01 | 2025-09-01 | 750 | TRUE | TRUE | 1
hotel.f | 2025-09-02 | 2025-10-17 | 70 | TRUE | TRUE | 1
hotel.pm | 2025-01-01 | 2025-09-01 | 80 | TRUE | TRUE | 1
hotel.pf | 2025-09-02 | 2025-10-17 | 10 | TRUE | TRUE | 1
hotel.sm | 2025-01-01 | 2025-09-01 | 15 | TRUE | TRUE | 1
hotel.sf | 2025-09-02 | 2025-10-17 | 5 | TRUE | TRUE | 1
india.m | 2025-01-01 | 2025-10-01 | 1100 | TRUE | TRUE | 1
india.f | 2025-10-02 | 2025-11-01 | 200 | TRUE | TRUE | 1
india.pm | 2025-01-01 | 2025-10-01 | 130 | TRUE | TRUE | 1
india.pf | 2025-10-02 | 2025-11-01 | 25 | TRUE | TRUE | 1
india.sm | 2025-01-01 | 2025-10-01 | 30 | TRUE | TRUE | 1
india.sf | 2025-10-02 | 2025-11-01 | 12 | TRUE | TRUE | 1
juliet.e | 2025-02-10 | 2025-02-27 | 10 | TRUE | TRUE | 1
juliet.m | 2025-02-28 | 2025-06-30 | 450 | TRUE | TRUE | 1
juliet.f | 2025-07-01 | 2025-08-15 | 35 | TRUE | TRUE | 1
juliet.pe | 2025-02-10 | 2025-02-27 | 10 | TRUE | TRUE | 1
juliet.pm | 2025-02-28 | 2025-06-30 | 50 | TRUE | TRUE | 1
juliet.pf | 2025-07-01 | 2025-08-15 | 5 | TRUE | TRUE | 1
juliet.se | 2025-02-10 | 2025-02-27 | 10 | TRUE | TRUE | 1
juliet.sm | 2025-02-28 | 2025-06-30 | 10 | TRUE | TRUE | 1
juliet.sf | 2025-07-01 | 2025-08-15 | 5 | TRUE | TRUE | 1
kilo.e | 2025-03-01 | 2025-03-24 | 20 | TRUE | TRUE | 1
kilo.m | 2025-03-25 | 2025-08-01 | 550 | TRUE | TRUE | 1
kilo.f | 2025-08-02 | 2025-09-16 | 40 | TRUE | TRUE | 1
kilo.pe | 2025-03-01 | 2025-03-24 | 10 | TRUE | TRUE | 1
kilo.pm | 2025-03-25 | 2025-08-01 | 50 | TRUE | TRUE | 1
kilo.pf | 2025-08-02 | 2025-09-16 | 5 | TRUE | TRUE | 1
kilo.se | 2025-03-01 | 2025-03-24 | 15 | TRUE | TRUE | 1
kilo.sm | 2025-03-25 | 2025-08-01 | 10 | TRUE | TRUE | 1
kilo.sf | 2025-08-02 | 2025-09-16 | 5 | TRUE | TRUE | 1
lima.m | 2025-04-20 | 2025-11-01 | 1050 | TRUE | TRUE | 1
lima.f | 2025-11-02 | 2025-11-30 | 120 | TRUE | TRUE | 1
lima.pm | 2024-04-20 | 2025-11-01 | 100 | TRUE | TRUE | 1
lima.pf | 2025-11-02 | 2025-11-30 | 20 | TRUE | TRUE | 1
lima.sm | 2024-04-20 | 2025-11-01 | 10 | TRUE | TRUE | 1
lima.sf | 2025-11-02 | 2025-11-30 | 5 | TRUE | TRUE | 1
mike.e | 2025-04-10 | 2025-04-20 | 10 | TRUE | TRUE | 1
mike.m | 2025-04-25 | 2025-09-25 | 450 | TRUE | TRUE | 1
mike.f | 2025-09-26 | 2025-10-30 | 60 | TRUE | TRUE | 1
mike.pe | 2025-04-10 | 2025-04-20 | 10 | TRUE | TRUE | 1
mike.pm | 2025-04-21 | 2025-09-25 | 50 | TRUE | TRUE | 1
mike.pf | 2025-09-26 | 2025-10-30 | 5 | TRUE | TRUE | 1
mike.se | 2025-04-10 | 2025-04-20 | 15 | TRUE | TRUE | 1
mike.sm | 2025-04-21 | 2025-09-25 | 10 | TRUE | TRUE | 1
mike.sf | 2025-09-26 | 2025-10-30 | 5 | TRUE | TRUE | 1
november.e | 2025-05-26 | 2025-06-14 | 10 | TRUE | TRUE | 1
november.m | 2025-06-15 | 2025-12-30 | 550 | TRUE | TRUE | 1
november.f | 2025-12-31 | 2026-01-31 | 30 | TRUE | TRUE | 1
november.pe | 2025-05-26 | 2025-06-14 | 10 | TRUE | TRUE | 1
november.pm | 2025-06-15 | 2025-12-30 | 55 | TRUE | TRUE | 1
november.pf | 2025-12-31 | 2026-01-31 | 5 | TRUE | TRUE | 1
november.se | 2025-05-26 | 2025-06-14 | 10 | TRUE | TRUE | 1
november.sm | 2025-06-15 | 2025-12-30 | 10 | TRUE | TRUE | 1
november.sf | 2025-12-31 | 2026-01-31 | 5 | TRUE | TRUE | 1
oscar.e | 2025-06-25 | 2025-07-09 | 15 | TRUE | TRUE | 1
oscar.m | 2025-07-10 | 2025-12-30 | 600 | TRUE | TRUE | 1
oscar.f | 2025-12-31 | 2026-01-31 | 40 | TRUE | TRUE | 1
oscar.pe | 2025-06-25 | 2025-07-09 | 15 | TRUE | TRUE | 1
oscar.pm | 2025-07-10 | 2025-12-30 | 70 | TRUE | TRUE | 1
oscar.pf | 2025-12-31 | 2026-01-31 | 10 | TRUE | TRUE | 1
oscar.se | 2025-06-25 | 2025-07-09 | 10 | TRUE | TRUE | 1
oscar.sm | 2025-07-10 | 2025-12-30 | 10 | TRUE | TRUE | 1
oscar.sf | 2025-12-31 | 2026-01-31 | 8 | TRUE | TRUE | 1
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?
Note on G1: Are date OK?

## links
Expert | Task | TRUE | TRUE
PM.Daniel | alpha.pm | 1 | 1
PM.Daniel | alpha.pf | 1 | 1
PM.Daniel | beta.pm | 1 | 1
PM.Daniel | beta.pf | 1 | 1
PM.Angel | charlie.pm | 1 | 1
PM.Angel | charlie.pf | 1 | 1
PM.Angel | delta.pm | 1 | 1
PM.Angel | delta.pf | 1 | 1
PM.Lisa | echo.pm | 1 | 1
PM.Lisa | echo.pf | 1 | 1
PM.Lisa | foxtrot.pm | 1 | 1
PM.Lisa | foxtrot.pf | 1 | 1
PM.Lisa | golf.pm | 1 | 1
PM.Lisa | golf.pf | 1 | 1
PM.Lisa | hotel.pm | 1 | 1
PM.Lisa | hotel.pf | 1 | 1
PM.Daniel | india.pm | 1 | 1
PM.Daniel | india.pf | 1 | 1
PM.Angel | juliet.pe | 1 | 1
PM.Angel | juliet.pm | 1 | 1
PM.Angel | juliet.pf | 1 | 1
PM.Lisa | kilo.pe | 1 | 1
PM.Lisa | kilo.pm | 1 | 1
PM.Lisa | kilo.pf | 1 | 1
PM.Lisa | lima.pm | 1 | 1
PM.Lisa | lima.pf | 1 | 1
PM.Angel | mike.pe | 1 | 1
PM.Angel | mike.pm | 1 | 1
PM.Angel | mike.pf | 1 | 1
PM.Angel | november.pe | 1 | 1
PM.Angel | november.pm | 1 | 1
PM.Angel | november.pf | 1 | 1
PM.Daniel | oscar.pe | 1 | 1
PM.Daniel | oscar.pm | 1 | 1
PM.Daniel | oscar.pf | 1 | 1
DEV.Paul | alpha.m | 1 | 1
DEV.Paul | alpha.f | 1 | 1
SA.Adrian | alpha.m | 1 | 1
SA.Adrian | alpha.f | 1 | 1
DEV.Hugo | alpha.m | 1 | 1
DEV.Hugo | alpha.f | 1 | 1
SA.Robert | beta.m | 1 | 1
SA.Robert | beta.f | 1 | 1
DEV.Frances | beta.m | 1 | 1
DEV.Frances | beta.f | 1 | 1
DEV.Tom | beta.m | 1 | 1
DEV.Tom | beta.f | 1 | 1
DEV.Charles | charlie.m | 1 | 1
DEV.Charles | charlie.f | 1 | 1
DEV.Francis | charlie.m | 1 | 1
DEV.Francis | charlie.f | 1 | 1
DEV.Carl | charlie.m | 1 | 1
DEV.Carl | charlie.f | 1 | 1
DEV.Paul | charlie.m | 1 | 1
DEV.Paul | charlie.f | 1 | 1
DEV.Lars | delta.m | 1 | 1
DEV.Lars | delta.f | 1 | 1
DEV.Martin | echo.m | 1 | 1
DEV.Martin | echo.f | 1 | 1
DEV.Michael | foxtrot.m | 1 | 1
DEV.Michael | foxtrot.f | 1 | 1
SA.Adrian | golf.m | 1 | 1
SA.Adrian | golf.f | 1 | 1
DEV.Hugo | golf.m | 1 | 1
DEV.Hugo | golf.f | 1 | 1
DEV.Francis | hotel.m | 1 | 1
DEV.Francis | hotel.f | 1 | 1
DEV.Martin | hotel.m | 1 | 1
DEV.Martin | hotel.f | 1 | 1
DEV.Michael | hotel.m | 1 | 1
DEV.Michael | hotel.f | 1 | 1
DEV.Paul | india.m | 1 | 1
DEV.Paul | india.f | 1 | 1
SA.Robert | india.m | 1 | 1
SA.Robert | india.f | 1 | 1
DEV.Lars | india.m | 1 | 1
DEV.Lars | india.f | 1 | 1
DEV.Charles | india.m | 1 | 1
DEV.Charles | india.f | 1 | 1
DEV.Tom | india.m | 1 | 1
DEV.Tom | india.f | 1 | 1
DEV.Carl | juliet.m | 1 | 1
DEV.Carl | juliet.f | 1 | 1
DEV.Hugo | juliet.m | 1 | 1
DEV.Hugo | juliet.f | 1 | 1
DEV.Martin | kilo.m | 1 | 1
DEV.Martin | kilo.f | 1 | 1
DEV.Francis | kilo.m | 1 | 1
DEV.Francis | kilo.f | 1 | 1
DEV.Paul | lima.m | 1 | 1
DEV.Paul | lima.f | 1 | 1
DEV.Frances | lima.m | 1 | 1
DEV.Frances | lima.f | 1 | 1
DEV.Michael | lima.m | 1 | 1
DEV.Michael | lima.f | 1 | 1
SA.Adrian | lima.m | 1 | 1
SA.Adrian | lima.f | 1 | 1
DEV.Martin | mike.m | 1 | 1
DEV.Martin | mike.f | 1 | 1
DEV.Michael | mike.m | 1 | 1
DEV.Michael | mike.f | 1 | 1
DEV.Carl | november.m | 1 | 1
DEV.Carl | november.f | 1 | 1
DEV.Hugo | november.m | 1 | 1
DEV.Hugo | november.f | 1 | 1
SA.Robert | oscar.m | 1 | 1
SA.Robert | oscar.f | 1 | 1
DEV.Tom | oscar.m | 1 | 1
DEV.Tom | oscar.f | 1 | 1
DEV.Michael | alpha.sm | 1 | 1
DEV.Michael | alpha.sf | 1 | 1
DEV.Carl | beta.sm | 1 | 1
DEV.Carl | beta.sf | 1 | 1
SA.Adrian | charlie.sm | 1 | 1
SA.Adrian | charlie.sf | 1 | 1
DEV.Hugo | delta.sm | 1 | 1
DEV.Hugo | delta.sf | 1 | 1
SA.Adrian | echo.sm | 1 | 1
SA.Adrian | echo.sf | 1 | 1
SA.Robert | foxtrot.sm | 1 | 1
SA.Robert | foxtrot.sf | 1 | 1
SA.Robert | golf.sm | 1 | 1
SA.Robert | golf.sf | 1 | 1
SA.Robert | hotel.sm | 1 | 1
SA.Robert | hotel.sf | 1 | 1
DEV.Charles | india.sm | 1 | 1
DEV.Charles | india.sf | 1 | 1
DEV.Charles | juliet.se | 1 | 1
DEV.Charles | juliet.sm | 1 | 1
DEV.Charles | juliet.sf | 1 | 1
DEV.Paul | kilo.se | 1 | 1
DEV.Paul | kilo.sm | 1 | 1
DEV.Paul | kilo.sf | 1 | 1
DEV.Tom | lima.sm | 1 | 1
DEV.Tom | lima.sf | 1 | 1
DEV.Frances | mike.se | 1 | 1
DEV.Frances | mike.sm | 1 | 1
DEV.Frances | mike.sf | 1 | 1
DEV.Frances | november.se | 1 | 1
DEV.Frances | november.sm | 1 | 1
DEV.Frances | november.sf | 1 | 1
DEV.Paul | oscar.se | 1 | 1
DEV.Paul | oscar.sm | 1 | 1
DEV.Paul | oscar.sf | 1 | 1
PM.Daniel | juliet.e | 1 | 1
PM.Daniel | kilo.e | 1 | 1
PM.Daniel | mike.e | 1 | 1
PM.Daniel | november.e | 1 | 1
PM.Daniel | oscar.e | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start day | End day | Lower | Upper | TRUE | TRUE | TRUE
PM.Daniel | alpha.pm | 2025-01-01 | 2025-04-01 | 0 | 1 | TRUE | TRUE | TRUE
PM.Daniel | alpha.pf | 2025-04-02 | 2025-05-02 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | beta.pm | 2025-01-01 | 2025-06-20 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | beta.pf | 2025-06-21 | 2025-08-05 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | india.pm | 2025-01-01 | 2025-10-01 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | india.pf | 2025-10-02 | 2025-11-01 | 1 | 2 | 1 | TRUE | 1
PM.Daniel | juliet.e | 2025-02-10 | 2025-02-27 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | kilo.e | 2025-03-01 | 2025-03-24 | 1 | 2 | 1 | TRUE | 1
PM.Daniel | mike.e | 2025-04-10 | 2025-04-20 | 1 | 2 | 1 | TRUE | 1
PM.Daniel | november.e | 2025-05-26 | 2025-06-14 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | oscar.e | 2025-06-25 | 2025-07-09 | 1 | 2 | 1 | TRUE | 1
PM.Daniel | oscar.pe | 2025-06-25 | 2025-07-09 | 1 | 2 | 1 | TRUE | 1
PM.Daniel | oscar.pm | 2025-07-10 | 2025-12-30 | 0 | 1 | 1 | TRUE | 1
PM.Daniel | oscar.pf | 2025-12-31 | 2026-01-31 | 0 | 1 | 1 | TRUE | 1
PM.Angel | charlie.pm | 2025-01-01 | 2025-06-05 | 0 | 1 | 1 | TRUE | 1
PM.Angel | charlie.pf | 2025-06-06 | 2025-07-06 | 0 | 1 | 1 | TRUE | 1
PM.Angel | delta.pm | 2025-01-01 | 2025-02-25 | 0 | 1 | 1 | TRUE | 1
PM.Angel | delta.pf | 2025-02-26 | 2025-04-12 | 0 | 1 | 1 | TRUE | 1
PM.Angel | juliet.pe | 2025-02-10 | 2025-02-27 | 0 | 1 | 1 | TRUE | 1
PM.Angel | juliet.pm | 2025-02-28 | 2025-06-30 | 0 | 1 | 1 | TRUE | 1
PM.Angel | juliet.pf | 2025-07-01 | 2025-08-15 | 0 | 1 | 1 | TRUE | 1
PM.Angel | mike.pe | 2025-04-10 | 2025-04-20 | 1 | 2 | 1 | TRUE | 1
PM.Angel | mike.pm | 2025-04-21 | 2025-09-25 | 0 | 1 | 1 | TRUE | 1
PM.Angel | mike.pf | 2025-09-26 | 2025-10-30 | 0 | 1 | 1 | TRUE | 1
PM.Angel | november.pe | 2025-05-26 | 2025-06-14 | 0 | 1 | 1 | TRUE | 1
PM.Angel | november.pm | 2025-06-15 | 2025-12-30 | 0 | 1 | 1 | TRUE | 1
PM.Angel | november.pf | 2025-12-31 | 2026-01-31 | 0 | 1 | 1 | TRUE | 1
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start day | End day | Lower | Upper | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start day | End day | Lower | Upper | TRUE | TRUE
PM.Daniel | 2025-01-01 | 2026-01-01 | 0 | 2 | TRUE | TRUE
PM.Angel | 2025-01-01 | 2026-01-01 | 0 | 2 | TRUE | TRUE
Note on F1: Valid expert?
Note on G1: Are date OK?

## ubsum
Expert | Task | Start day | End day | Lower | Upper | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## expert bounds
Expert | Start day | End day | Lower | Upper | TRUE | TRUE
PM.Daniel | 2025-01-01 | 2026-01-01 | 0 | 3 | TRUE | TRUE
PM.Angel | 2025-01-01 | 2026-01-01 | 0 | 2 | TRUE | TRUE
Note on F1: Valid expert?
Note on G1: Are date OK?

## invoicing periods
Name | Start day | End day | TRUE
January.2025 | 2024-12-11 | 2025-01-15 | TRUE
February.2025 | 2025-01-16 | 2025-02-13 | 1
March.2025 | 2025-02-14 | 2025-03-16 | 1
April.2025 | 2025-03-17 | 2025-04-14 | 1
May.2025 | 2025-04-15 | 2025-05-18 | 1
June.2025 | 2025-05-19 | 2025-06-18 | 1
July.2025 | 2025-06-19 | 2025-07-17 | 1
August.2025 | 2025-07-18 | 2025-08-17 | 1
September.2025 | 2025-08-18 | 2025-09-15 | 1
October.2025 | 2025-09-16 | 2025-10-15 | 1
November.2025 | 2025-10-16 | 2025-11-12 | 1
December.2025 | 2025-11-13 | 2025-12-11 | 1
Note on D1: Are date OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Daniel | January.2025 | 0 | 180 | TRUE | TRUE
PM.Daniel | February.2025 | 0 | 180 | 1 | 1
PM.Daniel | March.2025 | 0 | 180 | 1 | 1
PM.Daniel | April.2025 | 0 | 180 | 1 | 1
PM.Daniel | May.2025 | 0 | 180 | 1 | 1
PM.Daniel | June.2025 | 0 | 180 | 1 | 1
PM.Daniel | July.2025 | 0 | 180 | 1 | 1
PM.Daniel | August.2025 | 0 | 180 | 1 | 1
PM.Daniel | September.2025 | 0 | 180 | 1 | 1
PM.Daniel | October.2025 | 0 | 180 | 1 | 1
PM.Daniel | November.2025 | 0 | 180 | 1 | 1
PM.Daniel | December.2025 | 0 | 180 | 1 | 1
PM.Angel | January.2025 | 0 | 180 | 1 | 1
PM.Angel | February.2025 | 0 | 180 | 1 | 1
PM.Angel | March.2025 | 0 | 180 | 1 | 1
PM.Angel | April.2025 | 0 | 180 | 1 | 1
PM.Angel | May.2025 | 0 | 180 | 1 | 1
PM.Angel | June.2025 | 0 | 180 | 1 | 1
PM.Angel | July.2025 | 0 | 180 | 1 | 1
PM.Angel | August.2025 | 0 | 180 | 1 | 1
PM.Angel | September.2025 | 0 | 180 | 1 | 1
PM.Angel | October.2025 | 0 | 180 | 1 | 1
PM.Angel | November.2025 | 0 | 180 | 1 | 1
PM.Angel | December.2025 | 0 | 180 | 1 | 1
DEV.Paul | January.2025 | 0 | 180 | 1 | 1
DEV.Paul | February.2025 | 0 | 180 | 1 | 1
DEV.Paul | March.2025 | 0 | 180 | 1 | 1
DEV.Paul | April.2025 | 0 | 180 | 1 | 1
DEV.Paul | May.2025 | 0 | 180 | 1 | 1
DEV.Paul | June.2025 | 0 | 180 | 1 | 1
DEV.Paul | July.2025 | 0 | 180 | 1 | 1
DEV.Paul | August.2025 | 0 | 180 | 1 | 1
DEV.Paul | September.2025 | 0 | 180 | 1 | 1
DEV.Paul | October.2025 | 0 | 180 | 1 | 1
DEV.Paul | November.2025 | 0 | 180 | 1 | 1
DEV.Paul | December.2025 | 0 | 180 | 1 | 1
SA.Adrian | January.2025 | 0 | 180 | 1 | 1
SA.Adrian | February.2025 | 0 | 180 | 1 | 1
SA.Adrian | March.2025 | 0 | 180 | 1 | 1
SA.Adrian | April.2025 | 0 | 180 | 1 | 1
SA.Adrian | May.2025 | 0 | 180 | 1 | 1
SA.Adrian | June.2025 | 0 | 180 | 1 | 1
SA.Adrian | July.2025 | 0 | 180 | 1 | 1
SA.Adrian | August.2025 | 0 | 180 | 1 | 1
SA.Adrian | September.2025 | 0 | 180 | 1 | 1
SA.Adrian | October.2025 | 0 | 180 | 1 | 1
SA.Adrian | November.2025 | 0 | 180 | 1 | 1
SA.Adrian | December.2025 | 0 | 180 | 1 | 1
SA.Robert | January.2025 | 0 | 180 | 1 | 1
SA.Robert | February.2025 | 0 | 180 | 1 | 1
SA.Robert | March.2025 | 0 | 180 | 1 | 1
SA.Robert | April.2025 | 0 | 180 | 1 | 1
SA.Robert | May.2025 | 0 | 180 | 1 | 1
SA.Robert | June.2025 | 0 | 180 | 1 | 1
SA.Robert | July.2025 | 0 | 180 | 1 | 1
SA.Robert | August.2025 | 0 | 180 | 1 | 1
SA.Robert | September.2025 | 0 | 180 | 1 | 1
SA.Robert | October.2025 | 0 | 180 | 1 | 1
SA.Robert | November.2025 | 0 | 180 | 1 | 1
SA.Robert | December.2025 | 0 | 180 | 1 | 1
DEV.Hugo | January.2025 | 0 | 180 | 1 | 1
DEV.Hugo | February.2025 | 0 | 180 | 1 | 1
DEV.Hugo | March.2025 | 0 | 180 | 1 | 1
DEV.Hugo | April.2025 | 0 | 180 | 1 | 1
DEV.Hugo | May.2025 | 0 | 180 | 1 | 1
DEV.Hugo | June.2025 | 0 | 180 | 1 | 1
DEV.Hugo | July.2025 | 0 | 180 | 1 | 1
DEV.Hugo | August.2025 | 0 | 180 | 1 | 1
DEV.Hugo | September.2025 | 0 | 180 | 1 | 1
DEV.Hugo | October.2025 | 0 | 180 | 1 | 1
DEV.Hugo | November.2025 | 0 | 180 | 1 | 1
DEV.Hugo | December.2025 | 0 | 180 | 1 | 1
DEV.Frances | January.2025 | 0 | 180 | 1 | 1
DEV.Frances | February.2025 | 0 | 180 | 1 | 1
DEV.Frances | March.2025 | 0 | 180 | 1 | 1
DEV.Frances | April.2025 | 0 | 180 | 1 | 1
DEV.Frances | May.2025 | 0 | 180 | 1 | 1
DEV.Frances | June.2025 | 0 | 180 | 1 | 1
DEV.Frances | July.2025 | 0 | 180 | 1 | 1
DEV.Frances | August.2025 | 0 | 180 | 1 | 1
DEV.Frances | September.2025 | 0 | 180 | 1 | 1
DEV.Frances | October.2025 | 0 | 180 | 1 | 1
DEV.Frances | November.2025 | 0 | 180 | 1 | 1
DEV.Frances | December.2025 | 0 | 180 | 1 | 1
DEV.Tom | January.2025 | 0 | 180 | 1 | 1
DEV.Tom | February.2025 | 0 | 180 | 1 | 1
DEV.Tom | March.2025 | 0 | 180 | 1 | 1
DEV.Tom | April.2025 | 0 | 180 | 1 | 1
DEV.Tom | May.2025 | 0 | 180 | 1 | 1
DEV.Tom | June.2025 | 0 | 180 | 1 | 1
DEV.Tom | July.2025 | 0 | 180 | 1 | 1
DEV.Tom | August.2025 | 0 | 180 | 1 | 1
DEV.Tom | September.2025 | 0 | 180 | 1 | 1
DEV.Tom | October.2025 | 0 | 180 | 1 | 1
DEV.Tom | November.2025 | 0 | 180 | 1 | 1
DEV.Tom | December.2025 | 0 | 180 | 1 | 1
PM.Lisa | January.2025 | 0 | 180 | 1 | 1
PM.Lisa | February.2025 | 0 | 180 | 1 | 1
PM.Lisa | March.2025 | 0 | 180 | 1 | 1
PM.Lisa | April.2025 | 0 | 180 | 1 | 1
PM.Lisa | May.2025 | 0 | 180 | 1 | 1
PM.Lisa | June.2025 | 0 | 180 | 1 | 1
PM.Lisa | July.2025 | 0 | 180 | 1 | 1
PM.Lisa | August.2025 | 0 | 180 | 1 | 1
PM.Lisa | September.2025 | 0 | 180 | 1 | 1
PM.Lisa | October.2025 | 0 | 180 | 1 | 1
PM.Lisa | November.2025 | 0 | 180 | 1 | 1
PM.Lisa | December.2025 | 0 | 180 | 1 | 1
DEV.Charles | January.2025 | 0 | 180 | 1 | 1
DEV.Charles | February.2025 | 0 | 180 | 1 | 1
DEV.Charles | March.2025 | 0 | 180 | 1 | 1
DEV.Charles | April.2025 | 0 | 180 | 1 | 1
DEV.Charles | May.2025 | 0 | 180 | 1 | 1
DEV.Charles | June.2025 | 0 | 180 | 1 | 1
DEV.Charles | July.2025 | 0 | 180 | 1 | 1
DEV.Charles | August.2025 | 0 | 180 | 1 | 1
DEV.Charles | September.2025 | 0 | 180 | 1 | 1
DEV.Charles | October.2025 | 0 | 180 | 1 | 1
DEV.Charles | November.2025 | 0 | 180 | 1 | 1
DEV.Charles | December.2025 | 0 | 180 | 1 | 1
DEV.Francis | January.2025 | 0 | 180 | 1 | 1
DEV.Francis | February.2025 | 0 | 180 | 1 | 1
DEV.Francis | March.2025 | 0 | 180 | 1 | 1
DEV.Francis | April.2025 | 0 | 180 | 1 | 1
DEV.Francis | May.2025 | 0 | 180 | 1 | 1
DEV.Francis | June.2025 | 0 | 180 | 1 | 1
DEV.Francis | July.2025 | 0 | 180 | 1 | 1
DEV.Francis | August.2025 | 0 | 180 | 1 | 1
DEV.Francis | September.2025 | 0 | 180 | 1 | 1
DEV.Francis | October.2025 | 0 | 180 | 1 | 1
DEV.Francis | November.2025 | 0 | 180 | 1 | 1
DEV.Francis | December.2025 | 0 | 180 | 1 | 1
DEV.Carl | January.2025 | 0 | 180 | 1 | 1
DEV.Carl | February.2025 | 0 | 180 | 1 | 1
DEV.Carl | March.2025 | 0 | 180 | 1 | 1
DEV.Carl | April.2025 | 0 | 180 | 1 | 1
DEV.Carl | May.2025 | 0 | 180 | 1 | 1
DEV.Carl | June.2025 | 0 | 180 | 1 | 1
DEV.Carl | July.2025 | 0 | 180 | 1 | 1
DEV.Carl | August.2025 | 0 | 180 | 1 | 1
DEV.Carl | September.2025 | 0 | 180 | 1 | 1
DEV.Carl | October.2025 | 0 | 180 | 1 | 1
DEV.Carl | November.2025 | 0 | 180 | 1 | 1
DEV.Carl | December.2025 | 0 | 180 | 1 | 1
DEV.Lars | January.2025 | 0 | 180 | 1 | 1
DEV.Lars | February.2025 | 0 | 180 | 1 | 1
DEV.Lars | March.2025 | 0 | 180 | 1 | 1
DEV.Lars | April.2025 | 0 | 180 | 1 | 1
DEV.Lars | May.2025 | 0 | 180 | 1 | 1
DEV.Lars | June.2025 | 0 | 180 | 1 | 1
DEV.Lars | July.2025 | 0 | 180 | 1 | 1
DEV.Lars | August.2025 | 0 | 180 | 1 | 1
DEV.Lars | September.2025 | 0 | 180 | 1 | 1
DEV.Lars | October.2025 | 0 | 180 | 1 | 1
DEV.Lars | November.2025 | 0 | 180 | 1 | 1
DEV.Lars | December.2025 | 0 | 180 | 1 | 1
DEV.Martin | January.2025 | 0 | 180 | 1 | 1
DEV.Martin | February.2025 | 0 | 180 | 1 | 1
DEV.Martin | March.2025 | 0 | 180 | 1 | 1
DEV.Martin | April.2025 | 0 | 180 | 1 | 1
DEV.Martin | May.2025 | 0 | 180 | 1 | 1
DEV.Martin | June.2025 | 0 | 180 | 1 | 1
DEV.Martin | July.2025 | 0 | 180 | 1 | 1
DEV.Martin | August.2025 | 0 | 180 | 1 | 1
DEV.Martin | September.2025 | 0 | 180 | 1 | 1
DEV.Martin | October.2025 | 0 | 180 | 1 | 1
DEV.Martin | November.2025 | 0 | 180 | 1 | 1
DEV.Martin | December.2025 | 0 | 180 | 1 | 1
DEV.Michael | January.2025 | 0 | 180 | 1 | 1
DEV.Michael | February.2025 | 0 | 180 | 1 | 1
DEV.Michael | March.2025 | 0 | 180 | 1 | 1
DEV.Michael | April.2025 | 0 | 180 | 1 | 1
DEV.Michael | May.2025 | 0 | 180 | 1 | 1
DEV.Michael | June.2025 | 0 | 180 | 1 | 1
DEV.Michael | July.2025 | 0 | 180 | 1 | 1
DEV.Michael | August.2025 | 0 | 180 | 1 | 1
DEV.Michael | September.2025 | 0 | 180 | 1 | 1
DEV.Michael | October.2025 | 0 | 180 | 1 | 1
DEV.Michael | November.2025 | 0 | 180 | 1 | 1
DEV.Michael | December.2025 | 0 | 180 | 1 | 1
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date
2024-12-24
2024-12-25
2024-12-26
2025-01-01
2025-04-20
2025-05-01

## misc
Today | Hours per day | dpi | T:start | T:end | H:start | H:end | Solver | Last day | Is T:start OK? | Is T:end OK? | Is H:start OK? | Is H:end OK?
2024-12-30 | 8 | 150 | 2025-01-01 | 2026-01-31 | 2025-01-01 | 2026-01-31 | highs | 2026-01-31 | 1 | TRUE | TRUE | TRUE