## experts
Name | Comment
Alojzy | Main tasks p2.*
Bartłomiej | Main tasks p3.*
Franciszek | No main task
Paweł | Main tasks p4.*
Wojciech | Main tasks p5.*

## tasks
Name | Start | End | Work
p2.m | 2024-12-05 | 2025-04-02 | 670
p2.f | 2025-04-03 | 2025-04-30 | 128
p2.pf | 2025-05-01 | 2025-05-13 | 64
p3.m | 2024-12-14 | 2025-05-30 | 636
p3.f | 2025-05-31 | 2025-06-27 | 96
p3.pf | 2025-06-28 | 2025-07-11 | 64
p4.m | 2025-01-04 | 2025-06-20 | 1130
p4.f | 2025-06-21 | 2025-07-18 | 160
p4.pf | 2025-07-19 | 2025-08-03 | 64
p5.m | 2025-01-14 | 2025-05-12 | 680
p5.f | 2025-05-13 | 2025-06-09 | 128
p5.pf | 2025-06-10 | 2025-06-23 | 64
p6.m | 2025-02-15 | 2025-08-01 | 1130
p6.f | 2025-08-02 | 2025-08-29 | 160
p6.pf | 2025-08-30 | 2025-09-12 | 64

## links
Expert | Task
Alojzy | p2.m
Alojzy | p2.f
Alojzy | p2.pf
Bartłomiej | p3.m
Bartłomiej | p3.f
Bartłomiej | p3.pf
Paweł | p4.m
Paweł | p4.f
Paweł | p4.pf
Wojciech | p5.m
Wojciech | p5.f
Wojciech | p5.pf
Alojzy | p4.m
Bartłomiej | p4.m
Franciszek | p4.m
Wojciech | p4.m
Franciszek | p6.m
Franciszek | p6.f
Franciszek | p6.pf
Alojzy | p6.m
Bartłomiej | p6.m
Paweł | p6.m
Wojciech | p6.m

## xbday
Expert | Task | Start | End | Lower | Upper
Alojzy | p2.m | 2024-12-05 | 2025-04-02 | 7 | 8
Alojzy | p2.f | 2025-04-03 | 2025-04-30 | 6 | 7
Alojzy | p2.pf | 2025-05-01 | 2025-05-13 | 7 | 8
Bartłomiej | p3.m | 2024-12-14 | 2025-05-30 | 4 | 8
Bartłomiej | p3.f | 2025-05-31 | 2025-06-27 | 4 | 5
Bartłomiej | p3.pf | 2025-06-28 | 2025-07-11 | 6 | 7
Paweł | p4.m | 2025-01-04 | 2025-06-20 | 8 | 8
Paweł | p4.f | 2025-06-21 | 2025-07-18 | 0 | 8
Paweł | p4.pf | 2025-07-19 | 2025-08-03 | 6 | 7
Wojciech | p5.m | 2025-01-14 | 2025-05-12 | 8 | 8
Wojciech | p5.f | 2025-05-13 | 2025-06-09 | 6 | 7
Wojciech | p5.pf | 2025-06-10 | 2025-06-23 | 6 | 7
Alojzy | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8
Bartłomiej | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8
Franciszek | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8
Wojciech | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8
Franciszek | p6.m | 2025-02-15 | 2025-08-01 | 8 | 8
Franciszek | p6.f | 2025-08-02 | 2025-08-29 | 8 | 8
Franciszek | p6.pf | 2025-08-30 | 2025-09-12 | 6 | 7
Alojzy | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8
Bartłomiej | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8
Paweł | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8
Wojciech | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End
25.Jan | 2024-12-11 | 2025-01-15
25.Feb | 2025-01-16 | 2025-02-13
25.Mar | 2025-02-14 | 2025-03-16
25.Apr | 2025-03-17 | 2025-04-14
25.May | 2025-04-15 | 2025-05-18

## invoicing periods bounds
Expert | Period | Lower | Upper

## public holidays
Date
2024-12-25

## misc
Today | Hours per day | Solver | Last day
2024-11-20 | 8 | scip | 2025-09-12

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## gimg
Task's Gantt Chart | Width | Height | Dpi | Start | End | Barh:color | Barh:height | Barh:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2025-07-02 | #ff7f0e | 0.9 | 0.6 | TRUE | TRUE

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5